## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2195-swen-261-12-a TeamA
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | Hugh; 02/27; Passed |  | AbuBakr; 03/31; Passed
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | Hugh; 02/27; Passed |  | AbuBakr; 03/31; Passed
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | Hugh; 02/27; Passed |  | AbuBakr; 03/31; Passed
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | AbuBakr; 02/27; Passed |  | Hugh; 03/31; Passed
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | AbuBakr; 02/27; Passed |  | Hugh; 03/31; Passed
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | AbuBakr; 02/27; Passed |  | Hugh; 03/31; Passed
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | AbuBakr; 02/27; Passed |  | Hugh; 03/31; Passed
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | Aahish; 03/02; Passed |  | Aahish; 03/31; Passed
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | Aahish; 03/02; Passed |  | Aahish; 03/31; Passed
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | Aahish; 03/02; Passed |  | Aahish; 03/31; Passed
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | Aahish; 03/02; Passed |  | Aahish; 03/31; Passed
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | Aaron; 03/02; Passed |  | Aahish; 03/31; Passed
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | Aaron; 03/02; Passed |  | Aahish; 03/31; Passed
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | Aaron; 03/02; Passed |  | Aaron; 03/31; Passed
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | Aaron; 03/02; Passed |  | Aaron; 03/31; Passed
As a Player, I want to be able to move an eligible piece towards the opponent diagonally so I can better position my pieces. | Given it is my turn and a piece is eligible to move diagonally forward one space, when I drag and drop that piece to that space to move to, then the piece is moved and the turn changes. |  |  |  | AbuBakr; 03/31; Passed
| Given it is not my turn, when I try to drag a piece, then the piece is not moved and nothing happens. |  |  |  | AbuBakr; 03/31; Passed
| Given I could make a jump move, when I drag and drop a piece to an eligible location for a simple jump move, then the piece is not moved and nothing happens. |  |  |  | Hugh; 03/31; Passed
| Given it is my turn and a piece is eligible to move to a location, when I drag and drop that piece to that location, then that piece is not moved and nothing happens. |  |  |  | Hugh; 03/31; Passed
As a player, I want to be able to move an eligible piece in a jump over opponents diagonally towards the opponent so I can apture an enemy piece. | Given that it is my turn and my piece is able to move 'over' another piece without being blocked, when I drag and drop that piece to that space, then the piece is moved and the piece that is jumped over is removed and the turn changes |  |  |  | AbuBakr; 03/31; Passed
| Given it is not my turn, when I try to drag a piece, then the piece is not moved and nothing happens. |  |  |  | AbuBakr; 03/31; Passed
| Given it is my turn and a piece is not eligible to move to a location, when I drag and drop that piece to that location, then the piece is not moved and nothing happens. |  |  |  | Hugh; 03/31; Passed
As a player, I want to move an eligible piece in multiple jumps over opponent's pieces diagonally in a recursive fashion towards the opponent so I can capture multiple enemy pieces. | Given it is not my turn, when I try to drag a piece, then the piece is not moved and nothing happens. |  |  |  | AbuBakr; 03/31; Passed
| Given it is my turn and a piece is not eligible to move to a location, when I drag and drop that piece to that location, then the piece is not moved and nothing happens. |  |  |  | AbuBakr; 03/31; Passed
| Given that it is my turn and a piece is eligible to make a jump move, and after that move, make another jump move, when I drag and that piece to make the first jump move, then the piece is moved to the first jump location and I am forced to continue to make jump moves with that piece until I cannot make another jump move. |  |  |  | Hugh; 03/31; Passed
| Given I made a multiple jump move, when I finish the last jump move, then the turn changes. |  |  |  | Hugh; 03/31; Passed
As a player who won the game, I want to see the results of the completed game so I can know who won. | Given the opponent has no pieces, when I do nothing, then the opponent loses the game and I win the game and both players leave the game. |  |  |  | Aaron; 03/31; Passed
As a player who lost the game, I want to see the result of a completed game so I can know who won. | Given I have no piece, when I do nothing, then the opponent wins the game and I lose the game and both players leave the game. |  |  |  | Aaron; 03/31; Passed
As a player, I want to be able to choose to surrender a game so I can end the game early when I'm don’t playing. | Given I am in game, when I click resign, I lose the match and the opponent wins the match and both players leave the game. |  |  |  | Aaron; 03/31; Passed
As a player with a piece in the final row, I want to be forced to king my piece when the piece reaches the row closest to my opponent, so that I follow the rules of the game | Given it is my turn and a piece is eligible to move to the final row, when I drag and drop the piece to the final row, then the piece is kinged.
Given it is not my turn, when I try to drag a piece, then the piece is not moved and nothing happens.
Given it is my turn and a piece is not eligible to move to the final row, when I drag and drop the piece to the final row, then the piece is not moved and nothing happens.
As a player with a kinged piece, I want to complete a single move, a single jump move, or multiple jump moves with kinged pieces but towards my side of the board so I can reposition or capture opponents pieces with my kinged piece. | Given it is my turn and my piece I am trying to move is kinged and is eligible for a backward simple move, single jump move or backwards multiple jump move, when I drag and drop that piece to that space, then piece is moved to that space and the turn changes.
Given I could make a jump move, when I drag and drop a piece to an eligible location for a simple jump move, then the piece is not moved and nothing happens.
Given it is my turn and a piece is not eligible to move to a location, when I drag and drop that piece to that location, then the piece is not moved and nothing happens.
Given it is my turn and a piece is not eligible to move to a location, when I drag and drop that piece to that location, then the piece is not moved and nothing happens.